## Sheet1
Task Name | Start Date | End Date | Duration (Days) | Dependency | Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
PROG6212 Portfolio of Evidence | 2025-09-15 | 2025-12-15 | 91 |  | All | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Part 1: Planning & Prototype (100 Marks) | 2025-09-15 | 2025-10-12 | 28 |  | Part 1 | X | X | X | X
Requirements Analysis & Research | 2025-09-15 | 2025-09-17 | 3 |  | Part 1 | X
Design Documentation | 2025-09-18 | 2025-09-22 | 5 | 4 | Part 1 |  | X
UML Class Diagram Creation | 2025-09-23 | 2025-09-26 | 4 | 5 | Part 1 |  |  | X
Project Plan Development | 2025-09-27 | 2025-10-01 | 3 | 6 | Part 1 |  |  |  | X
GUI/UI Prototype Design | 2025-10-02 | 2025-10-07 | 6 | 7 | Part 1 |  |  |  |  | X
GitHub Repository Setup | 2025-10-08 | 2025-10-09 | 2 | 8 | Part 1 | [5 empty] | X
Part 1 Report Writing | 2025-10-10 | 2025-10-12 | 3 | 9 | Part 1 | [6 empty] | X
Part 1 Submission | 2025-10-12 | 2025-10-12 | 0 | 10 | Part 1 | [6 empty] | MILESTONE
Part 2: Web Application Development (100 Marks) | 2025-10-13 | 2025-11-16 | 35 |  | Part 2 | [6 empty] | X | X | X | X | X | X | X
Database Implementation | 2025-10-13 | 2025-10-17 | 5 | 11 | Part 2 | [6 empty] | X | X
Claim Submission Feature | 2025-10-18 | 2025-10-25 | 6 | 12 | Part 2 | [7 empty] | X | X
Document Upload Functionality | 2025-10-26 | 2025-10-30 | 3 | 13 | Part 2 | [8 empty] | X | X
Verification & Approval Views | 2025-10-31 | 2025-11-06 | 5 | 14 | Part 2 | [9 empty] | X | X
Claim Status Tracking System | 2025-11-07 | 2025-11-10 | 4 | 15 | Part 2 | [10 empty] | X | X
Unit Testing Implementation | 2025-11-11 | 2025-11-13 | 3 | 16 | Part 2 | [11 empty] | X | X
YouTube Demo Video Creation | 2025-11-14 | 2025-11-15 | 2 | 17 | Part 2 | [12 empty] | X
Part 2 Submission | 2025-11-16 | 2025-11-16 | 0 | 18 | Part 2 | [12 empty] | MILESTONE
Part 3: Automation & Enhancement (100 Marks) | 2025-11-17 | 2025-12-12 | 26 |  | Part 3 | [12 empty] | X | X
Lecturer View Auto-Calculation | 2025-11-17 | 2025-11-21 | 5 | 19 | Part 3 | [12 empty] | X | X
Coordinator/Manager Automation | 2025-11-22 | 2025-11-28 | 5 | 20 | Part 3 | [12 empty] | X | X
HR View & Report Generation | 2025-11-29 | 2025-12-04 | 4 | 21 | Part 3 | [12 empty] | X | X
Advanced Testing & Validation | 2025-12-05 | 2025-12-07 | 3 | 22 | Part 3 | [12 empty] | X | X
PowerPoint Presentation Creation | 2025-12-08 | 2025-12-10 | 3 | 23 | Part 3 | [13 empty] | X | X
Final YouTube Video | 2025-12-11 | 2025-12-12 | 2 | 24 | Part 3 | [13 empty] | X | X
Part 3 Submission | 2025-12-12 | 2025-12-12 | 0 | 25 | Part 3 | [13 empty] | MILESTONE | X
Final Preparation & Buffer | 2025-12-13 | 2025-12-15 | 3 |  | Final | [13 empty] | X | X
Final Review & Quality Check | 2025-12-13 | 2025-12-14 | 2 | 26 | Final | [13 empty] | X | X
Final POE Submission | 2025-12-15 | 2025-12-15 | 0 | 27 | Final | [13 empty] | MILESTONE | X